## Annex I Action Plan 2014
Action Plan of Colleges for 2014
Topic |  | Actions required from competent authorities | Deadline | Status of Action | Summary of progress/accomplishment | Actions required from EBA staff | Deadline | Status of Action | Summary of progress/accomplishment
Cross-border banking groups in EEA | EEA cross border banking groups | Competent authorities to notify EBA on the cross border banking groups under their jurisdiction | February | Completed | The information has been provided accordingly. | To collect and maintain a database with all EEA cross border banking groups | Ongoing | Completed | The database was created and updated on an ongoing basis.
|  | Consolidating supervisors to notify EBA on the establishment of colleges for the banking groups meeting CRD requirements |  | Completed |  | To collect and maintain a database with all colleges established in EEA |  | Completed
|  | For colleges that have not been set up competent authorities to notify the reasons of non-establishment and intended follow-up actions |  | Completed |  | To follow up on cases for which colleges have not been set up yet |  | Completed | EBA staff followed all cases and assisted NCAs individually where necessary.
| Cross-border banking groups operating in EEA with parent in a third country | Competent authorities to notify EBA on the cross-border banking groups with parent in a third country operating in their jurisdiction |  | Completed |  | To collect and maintain a database with all cross-border banking groups operating in EEA with parent in a third country |  | Completed | The database was created and updated on an ongoing basis.
|  | Consolidating supervisors to notify EBA on the establishment of colleges for cross-border banking groups operating in EEA with parent in a third country |  | Completed |  | To collect and maintain a database with all colleges for cross-border banking groups operating in EEA with parent in a third country |  | Completed
[6 empty] | To assess the options to organise sub-consolidated supervisory collaboration at the EEA level for cross-border banking groups operating in EEA with parent in a third country | February | Partially completed | EBA performed an assessment on the current coverage of the colleges established at the EEA level for non-EEA banking groups, and included one of these colleges in the list of colleges to be monitored on a thematic basis.
| Closely monitored colleges |  |  |  |  | To propose a selection of colleges that will be closely monitored based on the application of quantitative and qualitative criteria |  | Completed | The selection of colleges has been completed in March 2014 and the `2014 List of colleges for EBA monitoring` document has been provided to the BoS.
|  | Consolidating supervisors for closely monitored colleges to submit to EBA details on college composition, structure, and contact persons | March | Largely completed | The information has been provided for all but 2 colleges. | To collect and maintain a database with all information on EEA closely monitored colleges | Ongoing | Completed | Templates have been collected and mapping charts have been developed offering transparent overview on groups` structure.
| Transition to SSM |  |  |  |  | To provide support to SSM for the smooth transition of supervisory tasks |  | Completed | EBA supported colleges in the following ways: 1. Organised meetings - conference calls in a centralised way directly with ECB staff; 2. Provided information when attending college meetings in 2014; 3. Assisted colleges with individual queries.
[6 empty] | To provide support to SSM for the review of cooperation agreements in the re-establishment of colleges under the SSM |  | Completed | 1. EBA organised training on the draft technical standards on the functioning of supervisory colleges where the new Cooperation and Coordination Agreement has been described. 2. This topic was presented by the EBA at all college meetings in 2014.
|  | Consolidating supervisors to notify EBA on the amendments in college composition, cooperation agreements, and contact details following the transition to SSM supervision | Ongoing | Completed | The information has been provided accordingly. | To collect and update information on amendments in college composition, cooperation agreements, and contact details following the transition to SSM supervision |  | Completed | The central database has continuously been updated.
Regular college activities | College Meetings | Consolidating supervisors for closely monitored colleges to organise at least one physical meeting with the participants of the general colleges and notify EBA about these meetings as well as other forms of gatherings (e.g. telcos) | November | Completed | Only one college has not organised any physical meeting in 2014, due to significant restructuring which resulted in the termination of the college in the middle of the year. | To monitor organisation of college meetings and arrange for participation in relevant meetings. To provide feedback on college meetings. |  | Completed | The closely monitored colleges held a total of 51 physical meetings in 2014, of which 47 were attended by EBA staff. The meetings not attended by EBA staff were focused on very specific or technical topics. EBA staff provided structured feedback after each college meeting.
| Coordinated supervisory action plan | Consolidating supervisors for closely monitored colleges to prepare within the college the coordinated action plan for 2013, based on the results of the previous JRAD process and to submit the plan to the EBA | March | Largely completed | The coordinated supervisory action plans have been provided to the EBA for all but 4 colleges. | To collect and maintain a database with all college supervisory action plans, and follow up on the implementation of the action plans |  | Completed | Supervisory action plans were collected and filed, though 4 plans have not been received in spite of EBA repeated requests.
Regular college activities | JRAD process | New ITS on Capital and Liquidity Joint Decision:
[6 empty] | To provide ITS training targeted especially to all consolidating supervisors | To be determined | Completed | The training was held on 27-28 February on the ITS on insitutiton specific requirement.
[6 empty] | To provide detailed presentations on ITS guidelines and templates in all colleges attended by EBA staff | Ongoing | Completed | The topic was covered by the EBA standard presentation delivered at all college meetings.
Joint Risk Assessment and Joint Decision on capital:
|  | Consolidating supervisors for closely monitored colleges to submit to EBA the timeline for reaching joint decision on capital adequacy (as set out in the ITS, and respecting the one year cycle) prepared and agreed by the college. It is important to note that the legal requirement on fulfilling the joint decision within 12 months from the last joint decision should be respected. | Within 3 months after reaching the previous joint decision, but no later than March 2014 | Largely completed | Timelines have been submitted to the EBA for all but 3 colleges. | To monitor roll out of agreed timeline for reaching joint capital decision | Ongoing | Completed | EBA staff monitored whether the colleges followed the timeline and provided feedback and support in individual cases where it was necessary. Due to the transition to the SSM supervision many of the timelines had to be updated and adjusted throughout 2014.
|  | Consolidating supervisors for closely monitored college to submit to EBA the draft and final risk assessment and joint decision documents for capital | As per agreed timeline (final joint decision document no later than 12 months after previous joint decision) | Partially completed | Not all colleges submitted both the draft and the final risk assessment documents. Only 8 colleges submitted the final JD documents to EBA. | To monitor timely submission of draft and final risk assessment and joint decision documents |  | Completed | In cases where EBA received the documents, feedback has been provided to consoldiating supervisors. The feedback focused on the compliance of the documents with existing technical standards and other relevant guidelines.
Joint Decision on liquidity:
|  | Consolidating supervisors for closely monitored colleges to submit to EBA the timeline for reaching joint decision on liquidity adequacy (as set out in the ITS) prepared and agreed by the college. It is to be noted that this is a new requirement for colleges and joint liquidity decision needs to be reached by 31 December 2014 at latest. | February | Largely completed | 3 colleges have not submitted the mentioned timeline to the EBA. | To monitor roll out of agreed timeline for reaching joint liquidity decision | Ongoing | Completed | EBA staff monitored whether the colleges followed the timeline and provided feedback and support in individual cases where it was necessary. Due to the transition to the SSM supervision many of the timelines had to be updated and adjusted throughout 2014.
|  | Consolidating supervisors for closely monitored colleges to submit to EBA the draft and final risk assessment and joint decision documents for liquidity | As per agreed timeline (final joint decision document no later than end December 2014) | Partially completed | Not all colleges submitted both the draft and the final risk assessment documents. Only 8 colleges submitted the final JD documents to EBA by the end of the year. | To monitor timely submission of draft and final risk assessment and joint decision documents |  | Completed | In cases where EBA received the documents, feedback has been provided to consoldiating supervisors. The feedback focused on the compliance of the documents with existing technical standards and other relevant guidelines.
| Emergency plans | Consolidating supervisors for closely monitored colleges to submit to EBA updated college emergency plan as agreed by the college | Ongoing | Completed | Updated information was received from 6 colleges. To update the emergency plan was not a requirement, however if the colleges updated the plan it was provided to the EBA. | To collect and maintain a database with all college emergency plans |  | Completed | The central database has continuously been updated.
Regular college activities | Recovery plans | Consolidating supervisors for closely monitored colleges to submit to EBA a clear timeline for college discussions on recovery plans | March | Largely not completed | Only 6 colleges provided the mentioned timeline to the EBA. | To follow up on compliance with EBA recommendation on development and assessment of recovery plans |  | Completed | EBA reminded NCAs to submit the timeline for college discussions on recovery plans. Also a training on the Assessment of Recovery Plans was held on 20 March at the EBA premises.
AQR | Asset quality review coordinated by consolidating supervisors | Consolidating supervisors for closely monitored colleges to communicate to EBA an agreement on performance of AQR and timeline as agreed by the college | January | Partially completed | 7 colleges have not provided the mentioned timeline. | To follow up on compliance with EBA recommendation on AQR |  | Completed | EBA monitored the compliance with the EBA recommendation on AQR.
Capital preservation | Recommendation on the preservation of Core Tier 1 capital | Consolidating supervisors for closely monitored colleges to discuss capital plans and possible waivers with the supervisory college and communicate to EBA a timeline for further college discussions on this subject if any more are planned in 2014. | February | Completed | The vast majority of colleges held discussions on capital plans, however only 13 timelines were received by the EBA. | To follow up on compliance with EBA recommendation on capital preservation |  | Completed | EBA monitored the follow up by colleges of the capital preservation recommendation and attended the college interactions organised for this topic.
Secure information exchange | Secure information exchange between competent authorities | Competent authorities willing to use the EBA IT collaboration tool to express their interest to EBA | Ongoing | Completed | EBA continued to support and promote the use of the EBA IT Collaboration tool. | To promote the use of the EBA IT Collaboration tool |  | Completed | EBA ensured continuous user support of EBA IT Collaboration tool, and completed the transfer of the tool from the Banque de France to the EBA so that also the technical support of the tool is ensured by EBA since 15 December 2014.
[6 empty] | To provide training on the use of the tool to the competent authorities interested in adopting the tool |  | Completed
[6 empty] | To improve the technical support relevant for the use of the tool |  | Completed
Other colleges | Communication with other colleges | Consolidating supervisors to notify EBA of any changes in contact details | Ongoing | Completed | Details have been provided to EBA on an ongoing basis. | To maintain a contact list for the other colleges |  | Completed | The contact lists have continuously been updated.
[6 empty] | To establish regular updates on EBA policy work and home-host related issues for the other colleges on a 'group-basis' | By 28 March | Completed | The other colleges regularly received the EBA Colleges Newsletter with relevant policy updates and information on colleges functioning as well as risk products. 3 issues have been provided throughout 2014.