## Sheet1
CEBS Work Programme 2008 (accomplished timeline) | January | February | March | April | May | June | July | August | September | October | November | December
CEBS Meetings | March: 5; June: 13; October: 8; December: 4
I. Regulatory advice and other externally driven work
Liquidity | bar: January to October
Own funds | bar: January to March
Large Exposures | bar: January to March
National Discretions | bar: January to October
Analysis of the effects of the CRD in the economic cycle | bar: January to December
*
Supervisory reporting
- amendment to Corep guidelines: reporting frequency and remittance dates | bar: January to June
- streamlining of Finrep guidelines | bar: January to September
due to incorporation of CRD changes
- analysis of simplified reporting procedures -one entry point | bar: January to September
[9 empty] | * | final decision postponed to 2010
- use test of Corep
postponed to 2009, to allow for incorporation of the revised CRD changes
Transparency of securitization activities and structured products under the CRD | bar: January to June
*
Valuation and risk management | bar: January to June
Equivalence of third countries supervision (Swiss and US) | bar: January
Supervisory and sanctioning powers
Delegation of tasks | bar: January to June
Strengthening the application of the Level 3 guidelines, recommendations and standards | bar: January to June
[6 empty] | * | completion postponed to answer to EU Commission request on supervisory powers
Improvements of working procedures and decision making mechanisms | bar: January to June
II. CEBS own initiative work on supervisory convergence
Supervision of liquidity risk | bar: January to October
Pillar 2 implementation issues: economic capital models, diversification benefits and capital allocation, level of application of ICAAPs
- supervisory assessment of economic capital models
postponed due to other priorities related to the unfolding of the crisis
- guidance on diversification benefits arising from internal models
[10 empty] | * | finalisation in 2009
- range of practices paper for assessing economic capital models
postponed due to other priorities related to the unfolding of the crisis
- range of practices paper for assessing risk sensitive capital allocation
postponed due to other priorities related to the unfolding of the crisis
-statement on the level of application of ICAAP
CRD implementation issues: list of central counterparties | bar: January to February
work stopped due to other priorities relating to the unfolding of the crisis
CRD implementation issues: CRD transposition group's (CRDTG) queries | January: ongoing
ongoing
Operational risk
to be continued in 2009
Monitoring of minimum capital requirements under CRD | bar: January to December
*
Impact assessment | bar: January to June
Monitoring on accounting and auditing developments | January: ongoing
ongoing
Convergence of Pillar 3 implementation | bar: January to June
Maintenance of reporting frameworks | January: ongoing
ongoing
Supervisory disclosure
finalisation in 2009
Passport notifications
finalisation in 2009
III. Co-operation and information exchange issues
Operational networking | January: ongoing
ongoing
Cooperation in crisis situations | January: ongoing
| ongoing | [10 empty] | *
Cooperation with third countries' supervisors | January: ongoing
ongoing
IV. Developing tools and working procedures
Common training and staff exchanges | January: ongoing
ongoing
Peer review exercise | bar: January to December
finalisation in 2009
Mediation mechanism | January: ongoing
ongoing
Key:
1st deliverable | bar: January
Planned | bar: January to March
Accomplished | bar: January to March